## Current Risks
CLINICAL RISK LOG | [5 empty] | Risk Rating | Level | [8 empty] | Risk Rating | Level |  | Risk Rating | Level
[6 empty] | 1-3 | Low | [8 empty] | 1-3 | Low |  | 1-3 | Low
[6 empty] | 4-6 | Moderate | [8 empty] | 4-6 | Moderate |  | 4-6 | Moderate
[6 empty] | 8-12 | High | [8 empty] | 8-12 | High |  | 8-12 | High
[6 empty] | 15-25 | Extreme | [8 empty] | 15-25 | Extreme |  | 15-25 | Extreme
ID | Date Logged | Last Update | Logged By | System | Clinical Lead | Baseline Risk Likelihood /Impact / Rating |  |  | Risk/Issue | (Action/Resolution) Currently mitigated by | Mitigating Action | Action With | Timescale for resolution | Likelihood (1-5) | Impact (1-5) | Risk Rating (Calc Field) | Status | Comments | Risk Assessment at Resolution Likelihood /Impact / Rating
| 2013-07-29 |  | Marianne Taylor | Paper prescription chart Administration | Joanne Dickson | 5 | 3 | 15 | Paper chart needed for prescribing and administration of medicines. If charts are lost or not on the ward / with the patient, medicines administration may be delayed. Major implications for patient safety. | Initiatives to ensure staff return charts to the bedside. Increased ward based pharmacy service so charts don't leave the ward when medicines are supplied. | Introduce an electronic eMedicines system that replaces paper charts. |  | 12 months | 1 | 1 | 1 |  | Risk removed through the introduction of the eMedicines system as paper charts no longer used.
| 2013-07-29 |  | Marianne Taylor | Paper prescription chart Medicine supply | Marianne Taylor | 5 | 3 | 15 | Paper chart needed to write and verify medicines orders. If charts are lost or not on the ward / with the patient, medicines orders may be delayed. Major implications for patient safety. | Initiatives to ensure staff return charts to the bedside. Increased ward based pharmacy service so charts don't leave the ward when medicines are supplied. | Introduce an electronic eMedicines system that replaces paper charts.
| 2013-07-29 |  | Marianne Taylor | Paper prescription chart Prescribing | Stephen Dean | 5 | 3 | 15 | When a prescription chart is lost it must be rewritten. This task is difficult and time consuming without the previous chart to refer to. Risk of prescribing errors. Major impliactions for patient safety. | Initiatives to ensure staff return charts to the bedside. Increased ward based pharmacy service so charts don't leave the ward when medicines are supplied. | Introduce an electronic eMedicines system that replaces paper charts.
| 2013-07-29 |  | Marianne Taylor | Paper prescription chart Prescribing | Stephen Dean | 5 | 5 | 25 | Medicines allergies are manually checked at the point of prescribing. Patients receive medicines that they are allergic to when clinicians don't complete or check the allergy box or when they don't recognise a medicine as being part of a class of medicines to which the patient is allergic. This represents a totally unacceptable level or quality of treatment/service. | Campaigns to raise awareness of medicines allergy issues. Prescription chart redesigned to encourage documentation and checking of allergies. | Introduce an electronic eMedicines system that replaces paper charts and provides decision support at the point of prescribing, pharmacist verification and administration.
| 2013-07-29 |  | Marianne Taylor | Paper prescription chart Pharmacist verification | Marianne Taylor | 4 | 5 | 20 | Medicines allergies are manually checked at the point of pharmacist verification. Patients receive medicines that they are allergic to when clinicians don't complete or check the allergy box or when they don't recognise a medicine as being part of a class of medicines to which the patient is allergic. This represents a totally unacceptable level or quality of treatment/service. | Campaigns to raise awareness of medicines allergy issues. Prescription chart redesigned to encourage documentation and checking of allergies. | Introduce an electronic eMedicines system that replaces paper charts and provides decision support at the point of prescribing, pharmacist verification and administration.
| 2013-07-29 |  | Marianne Taylor | Paper prescription chart Administration | Joanne Dickson | 5 | 5 | 25 | Medicines allergies are manually checked at the point of administration. Patients receive medicines that they are allergic to when clinicians don't complete or check the allergy box or when they don't recognise a medicine as being part of a class of medicines to which the patient is allergic. This represents a totally unacceptable level or quality of treatment/service. | Campaigns to raise awareness of medicines allergy issues. Prescription chart redesigned to encourage documentation and checking of allergies. | Introduce an electronic eMedicines system that replaces paper charts and provides decision support at the point of prescribing, pharmacist verification and administration.
| 2013-07-29 |  | Marianne Taylor | Paper prescription chart Medicine supply | Marianne Taylor | 4 | 5 | 20 | Medicines allergies are manually checked when medicines are ordered or supplied. Patients receive medicines that they are allergic to when clinicians don't complete or check the allergy box or when they don't recognise a medicine as being part of a class of medicines to which the patient is allergic. This represents a totally unacceptable level or quality of treatment/service. | Campaigns to raise awareness of medicines allergy issues. Prescription chart redesigned to encourage documentation and checking of allergies. | Introduce an electronic eMedicines system that replaces paper charts and provides decision support at the point of prescribing, pharmacist verification and administration.
| 2013-07-29 |  | Marianne Taylor | Paper prescription chart Prescribing | Stephen Dean | 5 | 3 | 15 | Handwritten prescriptions can be difficult to read leading to wrong medicine, wrong dose, wrong route and wrong frequency errors. Major impliactions for patient safety. |  | Introduce an electronic eMedicines system that replaces paper charts.
| 2013-07-29 |  | Marianne Taylor | Paper prescription chart Administration | Joanne Dickson | 3 | 2 | 6 | Medicines administration that is recorded late on the chart may lead to extra doses being given the following day. Previous initials are used as a prompt rather than dose times circled by the prescriber. Minor implications for patient safety. |  | Introduce an electronic eMedicines system that replaces paper charts.
| 2013-07-29 |  | Marianne Taylor | Paper prescription chart Prescribing | Stephen Dean | 5 | 2 | 10 | Lack of prescriber knowledge can mean prescriptions lack essential details e.g. brand name, where using the wrong product puts the patient at risk of side effects or relapse; antibiotic indication and duration, where recording this information is a key part of antimicrobial stewardship to reduce resistance. Minor implications for patient safety. | Pharmacist verification of prescriptions | Introduce an electronic eMedicines system that replaces paper charts and provides decision support at the point of prescribing, pharmacist verification and administration.
| 2013-07-29 |  | Marianne Taylor | Paper prescription chart System integration |  | 3 | 1 | 3 | Prescribers are not familiar with all medicines and may need to look up information when prescribing. This may involve checking several sources e.g. BNF, Leeds Health Pathways before the prescription can be written. Peripheral element of treatment suboptimal. | Pharmacist presence on wards, Medicines Information Service | introduce an electronic eMedicines system that replaces paper charts links to electronic medicines information resources.
| 2013-07-29 |  | Marianne Taylor | Paper prescription chart System integration |  | 3 | 1 | 3 | Nurses are not familiar with all medicines and may need to look up information when administering medicines This may involve checking several sources e.g. BNF, Leeds Health Pathways before the prescription can be written. Peripheral element of treatment suboptimal. | Pharmacist presence on wards, Medicines Information Service | introduce an electronic eMedicines system that replaces paper charts links to electronic medicines information resources.
| 2013-07-29 |  | Marianne Taylor | Paper prescription chart Medicine supply | Marianne Taylor | 3 | 1 | 3 | If a medicine is prescribed that is not kept in the Trust it can be several hours before that is known by nursing and medical staff. Peripheral element of treatment suboptimal. |  | Introduce an electronic eMedicines system that replaces paper charts and is able to highlight where medicines are not readiliy available in the Trust.
| 2013-07-29 |  | Marianne Taylor | Paper prescription chart Prescribing | Stephen Dean | 5 | 3 | 15 | It is not always possible to confirm the patients medication history before prescribing. Patients may wait several days for all their regular medicines to be prescribed. Major implications for patient safety. | Pharmacy initiatives to reduce the time taken to prescribe regular medicines. | Introduce an electronic eMedicines system that replaces paper charts and improves the medicines history and medicines reconciliation process.
| 2013-07-29 |  | Marianne Taylor | Paper prescription chart General |  | 4 | 2 | 8 | Limited space for prescribing on charts so some patients have multiple charts. Some high risk medicines are prescribed on specific charts. If multiple charts become separated, essential information can be missed. Minor implications for patient safety. |  | Introduce an electronic eMedicines system that replaces paper charts.
| 2013-07-29 |  | Marianne Taylor | Paper prescription chart Prescribing | Stephen Dean | 4 | 2 | 8 | Paper charts must be rewritten every 2 weeks because space for administration is limited. Rewriting charts carries the risk of transcription errors. Minor implications for patient safety. | Pharmacists check transcribed charts. | Introduce an electronic eMedicines system that replaces paper charts.
| 2013-07-29 |  | Marianne Taylor | Paper prescription chart Administration | Joanne Dickson | 4 | 2 | 8 | Paper charts must be rewritten every 2 weeks because space for administration is limited. If not done quickly enough lack of space can disrupt medicines administration. Minor implications for patient safety. |  | Introduce an electronic eMedicines system that replaces paper charts.
| 2013-07-29 |  | Marianne Taylor | Paper prescription chart Medicine supply | Marianne Taylor | 3 | 3 | 5 | Medicines ordered on paper forms. The process is prone to transcription and dispensing errors. Major implications for patient safety. | Orders written and checked by 2 people before the medicine is supplied. | Introduce an electronic eMedicines system that replaces paper charts and supports the medicines order process.
| 2013-07-29 |  | Marianne Taylor | Paper prescription chart Medicine supply |  | 3 | 1 | 3 | Medicines ordered on paper forms. The need to transfer paper forms between wards and dispensary can delay medicines supply. Peripheral element of service suboptimal. |  | Introduce an electronic eMedicines system that replaces paper charts and supports the medicines order process.
| 2013-07-29 |  | Marianne Taylor | Paper prescription chart Medicine supply | Marianne Taylor | 3 | 1 | 3 | Medicines ordered on paper forms. It may be difficult for pharmacy and nursing staff to determine if something has been ordered or not. Peripheral element of service suboptimal. | Charts should be manually annotated when supply authorised. | Introduce an electronic eMedicines system that replaces paper charts and supports the medicines order process.
| 2013-07-29 |  | Marianne Taylor | Paper prescription chart Prescribing | Stephen Dean | 3 | 2 | 6 | Use of abbreviations on handwritten prescriptions increases the risk of medicines administration errors. Minor implications for patient safety. | Pharmacist verification of prescriptions - information clarified. | Introduce an electronic eMedicines system that replaces paper charts and contains a drug database.
| 2013-07-29 |  | Marianne Taylor | Paper prescription chart Documentation |  | 3 | 2 | 6 | Amendments to prescriptions or administration records can obscure important information and make prescriptions more difficult to read, increasing the risk of errors. Minor implications for patient safety. | Medicines Code and pharmacist Good Practice Guidance specifies how charts should be amended. Prescribers and pharmacy staff are informed of requirements at induction. | Introduce an electronic eMedicines system that replaces paper charts.
| 2013-07-29 |  | Marianne Taylor | Paper prescription chart Documentation |  | 5 | 2 | 10 | It can be difficult to identify the prescriber or pharmacist who has written or amended prescriptions. It may take time to determine who has written a prescription if a point needs to be clarified. The lack of audit trail makes investigation more difficult. Peripheral element of service suboptimal. |  | Introduce an electronic eMedicines system that replaces paper charts.
| 2013-07-29 |  | Marianne Taylor | Paper prescription chart Administration | Joanne Dickson | 5 | 1 | 5 | It can be difficult to identify the person who has administered a medicine. The lack of audit trail makes investigation more difficult. |  | Introduce an electronic eMedicines system that replaces paper charts.
| 2013-07-29 |  | Marianne Taylor | Paper prescription chart Information Governance |  | 3 | 2 | 6 | Unauthorised people (including patients) are able to write or amend prescriptions on charts or outpatient prescriptions. This may be difficult to detect. Minor implications for patient safety. | Prescription charts and outpatient prescription forms are "controlled stationary". | Introduce an electronic eMedicines system with robust user access control.
| 2013-07-29 |  | Marianne Taylor | Paper prescription chart Information Governance |  | 5 | 1 | 5 | Charts are kept at the patients' bedside - the information is not confidential. Failure to meet internal standards. |  | Introduce an electronic eMedicines system with robust user access control.
| 2013-07-29 |  | Marianne Taylor | Paper prescription chart Administration | Joanne Dickson | 4 | 2 | 8 | It is difficult to identify which doses are due. The risk of medicines omission is increased when more than one chart is in concurrent use. Minor implications for patient safety. |  | Introduce an electronic eMedicines system that replaces paper charts and prompts when medicines are due.
| 2013-07-29 |  | Marianne Taylor | Paper prescription chart Prescribing | Stephen Dean | 4 | 2 | 8 | Unintentional duplicate prescribing. The risk of this is increased when more than one chart is in concurrent use. Minor implications for patient safety. | Pharmacist verification of prescriptions. Nurse vigilance. | Introduce an electronic eMedicines system that replaces paper charts and provides decision support at the point of prescribing, pharmacist verification and administration.
| 2013-07-29 |  | Marianne Taylor | Paper prescription chart Prescribing | Stephen Dean | 5 | 2 | 10 | Medicines prescribed for administration by multiple routes where doses are not equivalent. Minor implications for patient safety. | Pharmacist verification of prescriptions. Medicines Code and medicines set out what is not acceptable practice. Part of prescribers induction. | Introduce an electronic eMedicines system that replaces paper charts and provides decision support at the point of prescribing, pharmacist verification and administration.
| 2013-07-29 |  | Marianne Taylor | Paper prescription chart Administration | Joanne Dickson | 5 | 1 | 5 | Medicines prescribed for administration by multiple routes. It is difficult to determine the route of administration for each individual dose because that information is not consistently recorded. Peripheral element of treatment suboptimal. |  | Introduce an electronic eMedicines system that replaces paper charts.
| 2013-07-29 |  | Marianne Taylor | Paper prescription chart Prescribing | Stephen Dean | 5 | 1 | 5 | Prescriptions with missing information: frequency, maximum daily dose. This leads to delayed administration or undocumented dose administration. Element of treatment suboptimal. | Pharmacist verification of prescriptions. Nurse vigilance. | Introduce an electronic eMedicines system that replaces paper charts.
| 2013-07-29 |  | Marianne Taylor | Paper prescription chart Administration | Joanne Dickson | 5 | 2 | 10 | Prescriptions for a specified course; risk of administration continuing beyond the intended stop date. Minor implications for patient safety. | Pharmacist and nurse review of prescriptions | Introduce an electronic eMedicines system that replaces paper charts.
| 2013-07-29 |  | Marianne Taylor | Paper prescription chart System integration |  | 3 | 2 | 6 | Some prescriptions must be checked against blood results and observations. Paper charts cannot be connected to electronic sources of information and prescribers are unable to benefit from prompts or reminders. Minor implications for patient safety. | Regular review by prescriber and pharmacist. MDT communication. | Introduce an electronic eMedicines system that can be integrated with the EPR.
| 2013-07-29 |  | Marianne Taylor | Paper prescription chart System integration |  | 3 | 2 | 6 | Some prescriptions must be checked against blood results and observations. Risk of continuing to administer medicines to patients when contraindicated or not required. | Regular review by prescriber and pharmacist. MDT communication. | Introduce an electronic eMedicines system that can be integrated with the EPR.
| 2013-07-29 |  | Marianne Taylor | Paper prescription chart Prescribing | Stephen Dean | 4 | 3 | 12 | Prescriptions must be manually checked for drug interactions at the point of prescribing. The complexity of this process puts the patient at risk of adverse events. Major implications for patient safety. |  | Introduce an electronic eMedicines system that replaces paper charts and provides decision support at the point of prescribing, pharmacist verification and administration.
|  |  | Marianne Taylor | Paper prescription chart Pharmacist verification | Marianne Taylor | 4 | 3 | 12 | Prescriptions must be manually checked for drug interactions at the point of pharmacist verification. The complexity of this process puts the patient at risk of adverse events. Major imp0lications for patient safety. |  | Introduce an electronic eMedicines system that replaces paper charts and provides decision support at the point of prescribing, pharmacist verification and administration.
| 2013-07-29 |  | Marianne Taylor | Paper prescription chart Administration | Joanne Dickson | 3 | 1 | 3 | Difficult to check charts before a medicine round to ensure all the doses are available. Medicines rounds may be interrupted when the medicine is not in the patient's locker or the drug trolley while the nurse locates a supply. Interruptions mean the athe round takes longer and increases the risk of administration errors. Element of service suboptiaml. |  | Introduce an electronic eMedicines system that supports the medicines administration process and prompts when medicines are due.
| 2013-07-29 |  | Marianne Taylor | Paper prescription chart Documentation | Joanne Dickson | 4 | 1 | 4 | The medicines administration record uses a number code to record when a medicine has not been given. Additional information should be recorded on the back of the chart but in many cases this doesn't happen. The lack of an audit trail makes investigation more difficult. Peripheral element of service suboptimal. |  | Introduce an electronic eMedicines system that supports the medicines administration process.
| 2013-07-29 |  | Marianne Taylor | Paper prescription chart Efficiency |  | 0 | 0 | 0 | A prescription chart may be used by only one person at a time. This reduces efficiency. |  | Introduce an electronic eMedicines system that replaces paper charts.
| 2013-07-29 |  | Marianne Taylor | Paper prescription chart Efficiency |  | 1 | 0 | 0 | After discharge the chart is filed in the patient's notes and leaves the ward. It may be difficult to respond to queries after discharge. Reduced efficiency. |  | Introduce an electronic eMedicines system that can be integrated with the EPR.
| 2013-07-29 |  | Marianne Taylor | Paper prescription chart Information Governance |  | 2 | 2 | 4 | The prescription chart may be filed in the wrong patients notes after discharge. Element of service suboptimal. |  | Introduce an electronic eMedicines system that can be integrated with the EPR.
| 2013-07-29 |  | Marianne Taylor | Paper prescription chart System integration |  |  |  |  | Prescriptions and allergy history may not be correct before they have been comprehensively checked against records held elsewhere e.g. PPM, Bluespier, SCR. Prescribers may lack the time and access. | Comprehensive medicine history checks and medicines reconciliation by pharmacy staff. Rolling out SCR access to prescribers | Introduce an electronic eMedicines system that can be integrated with the EPR.
| 2013-07-29 |  | Marianne Taylor | Paper prescription chart Administration | Joanne Dickson | 2 | 3 | 6 | Patient demographic details may be wrong (wrong addressograph) so medicines may be given to the wrong patient. Major implications for patient safety. |  | Introduce an electronic eMedicines system that replaces paper charts.
| 2013-07-29 |  | Marianne Taylor | Paper prescription chart Administration | Joanne Dickson | 2 | 3 | 6 | Drug chart does not highlight where there are patients with similar names on the ward. Medicines may be given to the wrong patient. Major implications for patient safety. | Use of warning stickers | Introduce an electronic eMedicines system that replaces paper charts.
| 2013-07-29 |  | Marianne Taylor | Paper prescription chart Documentation |  | 3 | 2 | 6 | If chart goes to Pharmacy the location recorded on the chart is used to identify where medicines are to be delivered to. Location recorded manually. Chart may have wrong ward location recorded on it after patient transfer. Medicine deliveries may go to the wrong location and be lost. Increased medicines waste and element of service suboptimal. | Medicines must be signed for on receipt on the ward. Medicines delivery record slips record the audit trail. To introduce electronic tracker. | Introduce an electronic eMedicines system that replaces paper charts and supports the medicines order process.
| 2013-07-29 |  | Marianne Taylor | Paper prescription chart Documentation |  | 3 | 2 | 6 | Chart used for communicating job requests via post-it notes, e.g. addition of regular medicines, the need for analgesics or laxatives. Notes can be misplaced, risk of jobs being missed. Minor implications for patient safety. | Local processes to improve communication of jobs. All communications documented in medical notes. | Introduce an electronic eMedicines system that replaces paper charts and supports the communication of medicines issues between healthcare professionals.
| 2013-07-29 |  | Marianne Taylor | Paper prescription chart Pharmacist verification | Marianne Taylor | 2 | 3 | 6 | Space on prescriptions charts is limited. Addition of information by pharmacists to support administration e.g. "tablets can be crushed" can obscure the prescription leading to administration and dispensing errors. Major implications for patient safety. |  | Introduce an electronic eMedicines system that replaces paper charts.
| 2013-07-29 |  | Marianne Taylor | Paper prescription chart Data use |  | 0 | 0 | 0 | The information recorded on paper charts cannot easily be used to monitor performance. |  | Introduce an electronic eMedicines system that is integrated such that activity and performance data is available and ready-to-use.
Click here for the NPSA Risk Matrix
Note on G6: Julie Batchelor: What is the baseline risk before implementation
Note on T6: Julie Batchelor: What is the risk assessment post resolution

## Resolved Risks
Resolved Risks
ID | Date Logged | Last Updated | Logged By | System | Risk/Issue | Action/Resolution | Mitigating Action | Action With | Timescale for resolution | Likelihood (1-5) | Impact (1-5) | Risk Rating (Calc Field) | Status

## NPSA Risk Matrix
NPSA Risk Matrix
Likelihood
Impact / Consequence |  |  | 1 | 2 | 3 | 4 | 5
|  |  | Rare | Unlikely | Possible | Likely | Almost Certain
| 5 | Catastrophic | 5 | 10 | 15 | 20 | 25
| 4 | Major | 4 | 8 | 12 | 16 | 20
| 3 | Moderate | 3 | 6 | 9 | 12 | 15
| 2 | Minor | 2 | 4 | 6 | 8 | 10
| 1 | Negligible | 1 | 2 | 3 | 4 | 5
Model Matrix
Likelihood score
|  |  | 1 | 2 | 3 | 4 | 5
|  | Descriptor | Rare | Unlikely | Possible | Likely | Almost certain
|  | Frequency How often might it/does it happen | This will probably never happen/recur | Do not expect it to happen/recur but it is possible it may do so | Might happen or recur occasionally | Will probably happen/recur but it is not a persisting issue | Will undoubtedly happen/recur,possibly frequently
Consequence score (severity levels) and examples of descriptors
|  |  | 1 | 2 | 3 | 4 | 5
|  | Domains | Negligible | Minor | Moderate | Major | Catastrophic
|  | Impact on the safety of patients, staff or public (physical/psychological harm) | Minimal injury requiring no/minimal intervention or treatment. | Minor injury or illness, requiring minor intervention | Moderate injury requiring professional intervention | Major injury leading to long-term incapacity/disability | Incident leading to death
|  |  | No time off work | Requiring time off work for >3 days | Requiring time off work for 4-14 days | Requiring time off work for >14 days | Multiple permanent injuries or irreversible health effects
|  |  |  | Increase in length of hospital stay by 1-3 days | Increase in length of hospital stay by 4-15 days | Increase in length of hospital stay by >15 days | An event which impacts on a large number of patients
[5 empty] | RIDDOR/agency reportable incident | Mismanagement of patient care with long-term effects
An event which impacts on a small number of patients
|  | Quality/complaints/audit | Peripheral element of treatment or service suboptimal | Overall treatment or service suboptimal | Treatment or service has significantly reduced effectiveness | Non-compliance with national standards with significant risk to patients if unresolved | Totally unacceptable level or quality of treatment/service
|  |  | Informal complaint/inquiry | Formal complaint (stage 1) | Formal complaint (stage 2) complaint | Multiple complaints/ independent review | Gross failure of patient safety if findings not acted on
|  |  |  | Local resolution | Local resolution (with potential to go to independent review) | Low performance rating | Inquest/ombudsman inquiry
|  |  |  | Single failure to meet internal standards | Repeated failure to meet internal standards | Critical report | Gross failure to meet national standards
|  |  |  | Minor implications for patient safety if unresolved | Major patient safety implications if findings are not acted on
Reduced performance rating if unresolved
|  | Human resources/ organisational development/staffing/ competence | Short-term low staffing level that temporarily reduces service quality (< 1 day) | Low staffing level that reduces the service quality | Late delivery of key objective/ service due to lack of staff | Uncertain delivery of key objective/service due to lack of staff | Non-delivery of key objective/service due to lack of staff
[5 empty] | Unsafe staffing level or competence (>1 day) | Unsafe staffing level or competence (>5 days) | Ongoing unsafe staffing levels or competence
[5 empty] | Low staff morale | Loss of key staff | Loss of several key staff
[5 empty] | Poor staff attendance for mandatory/key training | Very low staff morale | No staff attending mandatory training /key training on an ongoing basis
No staff attending mandatory/ key training
|  | Statutory duty/ inspections | No or minimal impact or breech of guidance/ statutory duty | Breech of statutory legislation | Single breech in statutory duty | Enforcement action | Multiple breeches in statutory duty
|  |  |  | Reduced performance rating if unresolved | Challenging external recommendations/ improvement notice | Multiple breeches in statutory duty | Prosecution
[6 empty] | Improvement notices | Complete systems change required
[6 empty] | Low performance rating | Zero performance rating
[6 empty] | Critical report | Severely critical report
|  | Adverse publicity/ reputation | Rumours | Local media coverage – | Local media coverage – | National media coverage with <3 days service well below reasonable public expectation | National media coverage with >3 days service well below reasonable public expectation. MP concerned (questions in the House)
|  |  |  | short-term reduction in public confidence | long-term reduction in public confidence
|  |  | Potential for public concern |  |  |  | Total loss of public confidence
Elements of public expectation not being met
|  | Business objectives/ projects | Insignificant cost increase/ schedule slippage | <5 per cent over project budget | 5–10 per cent over project budget | Non-compliance with national 10–25 per cent over project budget | Incident leading >25 per cent over project budget
|  |  |  | Schedule slippage | Schedule slippage | Schedule slippage | Schedule slippage
[6 empty] | Key objectives not met | Key objectives not met
|  | Finance including claims | Small loss Risk of claim remote | Loss of 0.1–0.25 per cent of budget | Loss of 0.25–0.5 per cent of budget | Uncertain delivery of key objective/Loss of 0.5–1.0 per cent of budget | Non-delivery of key objective/ Loss of >1 per cent of budget
|  |  |  | Claim less than £10,000 | Claim(s) between £10,000 and £100,000 | Claim(s) between £100,000 and £1 million | Failure to meet specification/ slippage
[6 empty] | Purchasers failing to pay on time | Loss of contract / payment by results
Claim(s) >£1 million
|  | Service/business interruption Environmental impact | Loss/interruption of >1 hour | Loss/interruption of >8 hours | Loss/interruption of >1 day | Loss/interruption of >1 week | Permanent loss of service or facility
|  |  | Minimal or no impact on the environment | Minor impact on environment | Moderate impact on environment | Major impact on environment | Catastrophic impact on environment

## Sheet1 (hidden)
Risk Assessment Scores
1
2
3
4
5