## Introduction
ePMA Readiness for Implementation Questionnaire
This questionnaire has been constructed to support Trusts prior to going live with an ePMA system. The purpose of the questionnaire is to give the Trust the opportunity to review the status of their project and to check that all of the key aspects have been completed or are in place in readiness to the ePMA system going live. The questionnaire aims to provide a pragmatic review of the status of the project. It does not include all aspects of an ePMA project, but the specific topics that should be considered prior to go live. Most of these are areas that could cause a problem at or after go live if they have not been considered.
Why is a Readiness for Implementation assessment needed? A successful implemention of an ePMA system is very complex and relies on many factors being in place. The success of the implementation / users acceptance of the new system can be negatively impacted by one or more of these factors not being ready, or not having been considered. This negative impact may result in poor user acceptance or, more importantly, reduced benefits and potentially impact patient safety.
How to Complete This questionnaire is designed to be completed in the format of a meeting / discussion so that all aspects of the status of the project can be explored. Often it can appear that a task is complete, however, on further discussion it can become clear that not all aspects have been considered. Ideally, the meeting should be carried out between the Trust's Project Manager, Pharmacy lead, IT lead, and Clinical lead (as appropriate for each organisation). Questions that are not relevant for ePMA implementations that are part of a full EPR implementation have been highlighted in the questionnaire.
Assessment of Readiness to implement In order to assess each Trust's 'readiness to implement' a Traffic Light system has been devised:
Showstopper - stop until resolved
Elements that should be completed before go live
Elements that need to be put in place, but will not prevent go live
All in place
The assessment of each question is based on the impact on the project if that project area has not been fully considered and established. In some instances 'go live' could proceed and the area resolved in parallel, in other instances the advice would be to resolve the issue before proceeding. THis assessement should be completed with the local project representatives and an action plan agreed.
Advice:

## Questionnaire
ePMA Readiness for Implementation Questionnaire
Trust
| Planned Go Live Date |  | Date of readiness review
Review carried out by:
| Review carried out with: |  | Role:
Overall review:
Category | Topic | Question | Comment | Not relevant for full EPR ePMA implementations | Response | Traffic Light
Technical | IT Acceptance Readiness Criteria | Does your Trust have IT acceptance readiness criteria? | Each Trust should have it's own IT acceptance readiness criteria. These are used to assess every IT implementation prior to go live.
Technical | IT Acceptance Readiness Criteria | Has the project passed your Trust's IT acceptance criteria?
Technical | IT - wireless Network | Have all areas of the clinical areas been checked to see if the wireless network works? i.e. all part of the ward to drug trolley will be positioned. Have all potential future areas also been checked for wireless? | Corners of wards / all side rooms All relevant clinics and specialist rooms | x part of overall EPR programme
Technical | IT - wireless Network | Has the wireless network been load tested to check it can cope with the additional work load that ePMA will require? | Especially areas of high use | x part of overall EPR programme
Technical | IT - local Devices | Has work been carried out to determine the right devices and right number of devices for each user / team? For 'go live' days, are there some spare devices in case the calculations for numbers required are wrong? | Ability to react quickly to increase or decrease requirements at go live will help the local 'buy in to the system. Also need to return to areas a few weeks post go live to see what is really required
Technical | IT - local Devices | Is there sufficient provision of power for the ePMA needs? | Check with estates if it will be possible to add extra plug sockets if needed, time scales for adding new sockets etc | x part of overall EPR programme
Technical | IT - local Devices | Are there enough plug sockets in the required places for charging the local devices in the clinical areas? | Think about access to PCs / screens whilst charging (rather than wasted technology). Also storage of devices and access for medical teams (? Charging stacks). | x part of overall EPR programme
Operational | IT - local Devices | Ownership of the devices: is a policy in place for teams to sign for / be responsible for the equipment they are given? |  | x part of overall EPR programme
Operational | IT - local Devices | Ownership of the devices: Who is responsible to replace devices if they have been lost, broken etc |  | x part of overall EPR programme
Operational | IT - local Devices | Ownership of the devices: Is there an agreed policy for checking that all devices are present on a ward, charged up etc |  | x part of overall EPR programme
Technical | IT - local Devices | Is there an agreed policy for the replacement or repair of devices? This policy should consider which devices / areas are critical to business as usual and the required timeframes for replacement or repair. It should also consider what stocks should be held to support critical business as usual and which can be reordered as required. | e.g. drug trolleys with integral PCs | x part of overall EPR programme
Technical | IT - integration | What Trust systems are you integrating/interfacing to? (add name of system): PAS (Patient Administration System) Order Communications Discharge letter Other ePMA systems (e.g. oncology; critical care) Pharmacy Robot Other pharmacy systems Other:
Technical | IT - integration | Where it is not possible to integrate / interface to another Trust system has the Trust got revised business processes/workarounds documented and communicated to staff?
Technical | IT - integration | Where it is not possible to integrate / interface to another Trust system, is there a forward plan to bring interfaces on board as and when required? Who owns this plan?
Technical | IT - integration | What integration testing have you carried out: - 1:1 testing between the ePMA system and each 3rd party system - full system testing | Need to think about all potential issues / eventualities
Technical | IT - integration | what on-going integration testing have you got planned? - 1:1 testing between the ePMA system and each 3rd party system (particularly as changes are made any of the systems) - full system testing - testing of new integration / interfaces
Technical | IT - integration | PAS / ePMA integration - have you considered all of the potential issues that integrating with your PAS may cause. | examples of processes to consider are listed below. This is not a complete list. mergers of patients who are already admitted transfers of patients between ePMA and paper prescribing wards PAS alterations carried out while a patient is admitted / an inpatient (i.e. a cancel admit / readmit as the admission had been completed wrongly may cause the patient to be lost off the ePMA system) ability to be able to prescribe for a patient before they are admitted (e.g. day patients; pre-meds; patients who come in for treatment but may not see the prescribers prior to treatment) patient is not 'transferred' from a ward to theatre (on PAS), therefore, meds due still appear on the drug round list - need a process on how to deal with this as meds may need to be given later | x part of overall EPR programme
System | Data Cleansing | If using an ePMA system that is part of a pre-existing system (e.g. a Pharmacy Stock Control system), have data cleansing activities taken place to ensure that any data that will adversely affect ePrescribing has been removed? | e.g. in some cases previous merging of patient records may have resulted in the patient NHS number being attached to the secondary and not the primary record. This may result in the incorrect record being picked up in JAC when the patient is admitted at a later date | x part of overall EPR programme
System | Configuration | is system configuration complete for the areas going live? | Including a check on consistency, accuracy of build (e.g. default doses, route, frequency), special requirements (e.g. restricted prescribing, PGDs etc)
System | Confguration | Have naming conventions been agreed (e.g. drugs with form and dose, routes) | So that prescribers know how to find items
Clinical | Configuration | Have the specific prescribing requirements for each area been configured, e.g. order sets, specialist medications and formulations, PGDs etc | Useful to get as much of this agreed pre go live as possible as will help with the 'buy in' of users (although they will develop their requirements as become more familiar with the system. An opportunity to standardise prescribing in some areas. Will favourites be available?
Clinical | Configuration | Signposting of items that are not going to be prescribed on the ePMA system (e.g. variable scale insulins, variable dose infusions, fluids)
Operational | Process | Have all departments that are part of a patient's journey for the clinical area going live been considered (e.g. endoscopy, nuclear medicine, theatres)? Have the processes for each department been documented, and are these available for future reference and training? | Prescribing and administration processes, viewing the drug chart, hardware etc Need to agree what prescribing is included as part of the electronic system and what stays on local / procedural records (e.g. peroperative prescribing; interventional radiology; endoscopy. Need to consider what happens pre and post procedure. Also most areas will need to be able to view the drug chart.
Clinical | Process | what process will be followed in an emergency / cardiac arrect situation (and similar) | Options may include: using the existing paper record retrospectively entering medications administered onto the ePMA entering data electronically in 'real-time'
Operational | Process | Has the order for roll out been considered, and the processes for transferring patients from the ePMA clinical area, to a paper prescribing area, and vice versa? | what areas are included and what isn't? Emergency Dept, Out-patients, Paediatics, Theatres. If not included need to consider processes as patients are transferred.
Clinical | Process | Have the specific processes / medication needs for each area going live been considered | e.g. what specialists work in the area; are drug trolleys used for drug rounds? Where do patients do? Are any specialist drugs / routes used, etc
Business | Process | Do you have rigorous change control process in place? |  | x part of overall EPR programme
Operational | Process | How will you manage system access? | Do you need to have done training before you are given access to the system? Who manages access to the system. How is this managed 24/7 | x part of overall EPR programme
Operational | Process | Is there an agreed process for capturing required system enhancements be captured and communicated with the supplier? |  | x part of overall EPR programme
Technical | Testing | Have local test scripts been written (for configuration, technical, and user testing)? Who has agreed and signed off these test scripts? | went to ensure test scripts have considered local needs and that Trusts are using localised sripts and not just supplier scripts.
Technical | Testing | What basic configuration testing (to check that all of the build as accurate, consistant, and works) has taken place? Have all scenarios been considered? What test scripts have you used? | e.g. all routes, formulations, order sets, etc
Technical | Testing | What technical testing has taken place? What test scripts have you used? | Integration, remote access, security / user access (e.g. the right person is logged on and recorded correctly), wireless access | x part of overall EPR programme
Technical | Testing | What end to end testing has taken place? What test scripts have you used? | Pre go live have a run through of sample prescriptions in the settings where the system will be used | x part of overall EPR programme
Technical | Testing | What user testing has taken place? What test scripts have you used? | Sessions for users to test whether the system works for them - may be done throughout the development process. Have they tried to 'break' the system? Good as a communication tool. Want to ensure test scripts ha
Business | Reporting | Have you defined the standard reports you will be producing?
Business | Reporting | Have you a process in place for agreeing and running ad hoc reports?
Business | Reporting | Have you got the required reporting skills in place for commencing the required reporting | Many benefits of ePMA is through being able to produce required reports | x part of overall EPR programme
Operational | Training | Has a training needs assessment been completed to determine what training is needed, the level of training and the form of training, for all relevant staff? | Training should be designed and developed considering the results of the training needs assessment | x part of overall EPR programme
Operational | Training | How will training be provided? Are the training materials and trainers ready? Have rooms been booked (if required) and cover for clinical areas to enable training? |  | x part of overall EPR programme
Operational | Training | For each area, has the Training Needs Assessment been carried out / considered with staff - including basic IT skills, skill mix on wards etc | Some Trusts widely use IT systems for all staff (e.g. rostering) but other organisations have low use and hence a % of staff with low level of skills or a phobia of systems. This needs to be identified and basic skills training carried out first if required. | x part of overall EPR programme
Operational | Training | Is there a training plan in place for each area / staff group going live to ensure training is mainly completed pre go live |  | x part of overall EPR programme
Operational | Training | Do you have a list of all of the staff requiring training for each area going live, so you can check whether enough people are trained to allow you to go live? | what is your minimum number of people to be trained in each area.
Operational | Training | How are you going to ensure your consultants also complete training? | encourages more junior staff; ? Use a different approach for different staff groups | x part of overall EPR programme
Operational | Training | How is competency being assessed at the end of training? What criteria are used to grant system access?
Operational | Training | what is your process for training and giving access to agency staff, locum doctors, visiting clinicians
Operational | Training | What is your approach for providing the required on-going training for new medical, nursing staff etc | e.g. inclusion on induction days, mandatory training | x part of overall EPR programme
Operational | Business Continuity | Are responsibilities clear for if there is a down time? | Are there standalone PCs for downtime? Is there a process for maintaining / checking these are on, have paper etc? Has this been communicated? Has the process been tested? | x part of overall EPR programme
Technical | Business Continuity | What is your back up solution for system downtime? | As soon as the system goes down, every ward, department and doctor using the system will call. Need to process to take the calls away from the people who need to be spending their time resolving the problem! Also need to be ensuring that users know that the problem is in hand and that there is a plan for resolution | x part of overall EPR programme
Operational | Business Continuity | Have business continuity and disaster recovery plans have been updated to reflect the introduction of the ePMA solution
Operational | Business Continuity | How will a problem / downtime be communicated to the users, along with expected resolution / timeframes etc? | Need to have a record of all prescription changes made to the paper record during downtime and make sure these are entered onto the electronic suystem before the system is made the primary system again. Need to be clear whose responsibility it is to do this (? nurse in charge on each ward). Need to agree how a retrospective record of the drug adminsitirations made during downtime will be entered onto the system. | x part of overall EPR programme
Operational | Business Continuity | if there has been a downtime, is there a clear process for ensuring all prescribing is up to date on the electronic system before there is a switch back to ePMA in each clinical area | There may be different process for the various causes of downtime, which may be planned or unplanned: - wireless net work not available - wired network not available - ePMA not available - patient not accessible (e.g. inteface with PAS not working) | x part of overall EPR programme
Operational | Business Continuity | Has a clear policy been communicated with the clinical areas of what to do if the ePMA system is not available.
Business | Governance | Have you got a 'go / no go' process in place where senior managers will agree that the Trust is ready to go live with the system? |  | x part of overall EPR programme
Business | Governance | Are the necessary governance procedures in place to make decisions on what changes will be made to the live system? | User groups; group to review issues and incidents. Escalation routes
Business | Governance | Do you have structures in place for escalating and reviewing issues as the system is rolled out? | local medical and nursing leads are vital to support the roll out
Business | Governance | Do you have clinical leadership who are prepared to actively support the rollout? |  | x part of overall EPR programme
Business | Governance | Do you have clinical leads for each area you are going live in to support the go live on a day to day basis | Need to understand how long project structures will be in place and when will become 'BAU'. Need to ensure that there are on-going governance arrangements to support the ePrescribing system, processes, and developments | x part of overall EPR programme
Business | Governance | Do you have governance arrangements in place for post go live / Business as Usual (BAU)? | Difficult to go live if insufficient junior medical staff on duty | x part of overall EPR programme
Operational | Go live | Has it been checked that there are sufficient staffing levels (both clinical and ePMA support) for each go live? | e.g. if surgical wards, what support is to be provided for the anaesthetics, in theatres and recovery etc
Operational | Go live | Has ePMA support been considered for out-lier areas? | e.g. when wider support needed (e.g. theatres)
Operational | Go live | Are extra floor walkers needed for any areas for provide support? | Need to make sure local support is available (e.g. clinical pharmacist, ward technician, junior doctor) as well as the specific ePMA and IT support. Ward ePMA lead / champion should be on duty to help with liaison
Operational | Go live | Is there a clear process for go live day: getting all prescriptions onto the electronic system and signed, providing support for drug rounds and prescribers etc. Has this been communicated to the users?
Operational | 24/7 support | How will both IM&T and ePMA support be provided, both for the periods of go live and on-going?
Operational | Communication | Do you have a communication strategy in place for letting all stakeholders know about the project, go live plans, what is expected of them etc |  | x part of overall EPR programme
Operational | Communication | Do you have a clear message, and is this endorsed (visibly) by your senior management? | Medical administrators, medical training lead | x part of overall EPR programme
Operational | Communication | Do you have a process in place to identify all of the medical staff in each area, how best to communicate with them, tell you of local regular meetings etc | Provide self help materials for users to reduce calls to the ePMA team | x part of overall EPR programme
Operational | Communications | Have quick reference guides/ standard operating procedures been written and made available to users (via Trust intranet, ePMA file on wards etc). These guidelines will provide step by step help for basic processes.
Operational | Communications | How will changes to the system; quick tips etc be communicated to all users
Traffic Light
Showstopper - stop until resolved
Elements that should be completed before go live
Elements that need to be put in place, but will not prevent go live
All in place

## Glossary
Term | Definition / Description
Change Control Process | A formal process used to ensure that changes to the ePMA system are introduced in a controlled and coordinated manner. It reduces the possibility that unnecessary changes will be introduced to a system without forethought, introducing faults into the system or undoing changes made by other users of software.
Configuration | The way the system is built; structure of the fields
Device | Generic term for the unit used by the end user to access the system; e.g. a laptop; PC; tablet; smart phone.
Discharge Letter / Discharge letter | A discharge summary is a letter written by the doctor caring for a patient in hospital. It contains important information about the hospital visit, including: reason for admission, results of any tests, treatment received, changes to medication, required follow up.
ePMA | electronic prescribing and medication administration
Integration | The process of linking together different computing systems and software applications physically or functionally, to act as a coordinated whole.
Load Testing | Load testing is the process of putting demand on a system or device and measuring its response. Load testing is performed to determine a system’s behavior under both normal and anticipated peak load conditions.
Order Communications / Order Comms | An IT system allowing the electronic ordering / requesting of, usually, clinical tests or referrals (e.g. pathology, radiology). Most systems also support the communication and acknowledgement of results
Order Set | A group of orders that can be ordered together as a single request.
Patient Administration System (PAS) | The PASrecords the patient's demographics (e.g. name, home address, date of birth) and details all patient contact with the hospital, both outpatient and inpatient.
Patient Group Direction (PGD) | PGDs are written instructions for the supply or administration of medicines to groups of patients who may not be individually identified before presentation for treatment

## Version Control
Developed by: Kathy Wallis, ePrescribing Domain Expert, NHS England; Programme Manager Wessex AHSN Ann Slee, ePrescribing Lead, NHS England March 2015
Version | Date | Comments
V0.1 Draft | 2014-12-09 | Initial Draft
V0.2 Draft | 2014-12-15 | Updated after review with Anne Joint, ePMA Project Manager, West Sussex Hospitals NHS Foundation Trust
V0.3 Draft | 2015-01-16 | Updated after review with Guy Roberts, HSCIC and with Shirley North, ePMA Project Manager, Guys and St Thomas's NHS Foundation Trust
V0.4 Draft | 2015-02-20 | Updated after review with Sue Thompson, Programme Head, Integrated Digital Care Technology Funds, Provider Support Directorate, Health and Social Care Information Centre (HSCIC)
V0.5 Draft | 2015-03-30 | Updated after scond review with Anne Joint, ePMA Project Manager, West Sussex Hospitals NHS Foundation Trust, and review with Steve Fairclough (CIO) and Colin Brown (CCOI) at University Hospitals of Morecambe Bay NHS Foundation Trust
V1.0 Final Version | 2015-03-30 | Circulated to Provider Facing Team HSCIC