## Sheet1
WHAT |  |  |  | WHAT |  | HOW |  | WHEN |  | WHO | STATUS | NOTES
Benefit Ref | Measure Ref | Benefit category (linked to business case) | Priority | Expected Benefit | Type | Measure | Method | Pre Go-Live | Post Go-Live | Owner
B1.1 | M1.1 | Patient Safety | High | Eliminate the prescribing of medicines that patients are allergic to. | Quantitative | Number of instances where medicines are prescribed to allergic patients | Extract data from Datix. Obtain data for all wards and generate a count by ward. Drug chart audit
[6 empty] | Number of instances where medicines are prevented from being prescribed to allergic patients | Generate an eP system report to count: 1. The number of times a user has tried to prescribe a drug the patient is allegic to. 2. The number of times an allergy warning has been issued. 3. The number of times an allergy warning has been overridden. | N/A | Y - when report available, at 3 monthly intervals.
[6 empty] | Number of allergic reactions caused by a medication in a given period. | Extract data from Datix. Obtain data for all wards and generate a count by ward. | Y (12 months data) | Y (6-12 months after go-live)
B1.1 | M1.2 | [5 empty] | Obtain casenotes from go-live wards. Extract information related to allergic reactions and count occurrences. | Y | N/A
B1.1 | M1.1 | Patient Safety |  | Eliminate inpatient transcription errors. | Quantitative | Number of transcription errors reported. | Extract data from Datix. Obtain data for all wards and generate a count by ward. | Y (12 months data) | Y (6-12 months after go-live)
B3.1 | M3.1 |  |  | Eliminate inpatient prescription to eDAN transcription errors. |  | Chart to eDAN transcription errors | Examine a 2 week snap shot of eDANs on go-live wards to count the number of transcription errors. | Y | Y (3 months after go-live) |  |  | Dependent on solution for eDANs
B5.1 | M5.1 | Patient Safety | High | Reduced prescribing errors. To include: wrong dose, wrong route, wrong frequency, unintended duplication, ambiguous or illegible prescriptions. | Quantitative | Number of prescribing errors | Extract data from Datix. Obtain data for all wards and generate a count by ward. | Y (12 months data) | Y (6-12 months after go-live)
[7 empty] | UHB IMPACT data collection tool - highlight prescribing errors that can be mitigated by eMedicines system This tool allows us to share information with other Trusts as part of a national project looking at the impact of eMedicines use. This tools needs to be used by a pharmacist. Data to be captured from paper charts pre go-live and post go-live | Y (TBC) | Y (6-12 months after go-live)
[7 empty] | Pharmacist intervention data | Y | Y (6-12 months after go-live)
[7 empty] | System report to highlight what warning messages are generated and the response from the prescriber. | N/A | Y - when report available, at 3 monthly intervals.
[7 empty] | System report of pharmacist activity | N/A | Y - when report available, at 3 monthly intervals.
|  | Clinical Effectiveness |  | The ability to target patients for clinical review. | Qualitative | eMeds user survey - how working practice changes as a result of implementation. | [5 empty] | Relates to pharmacist activity. Could there be similar benefits for medical staff?
|  | Clinical Effectiveness |  | Standardised prescribing via order sets. | Qualitative | eMeds user survey - how working practice changes as a result of implementation.
|  | Clinical Effectiveness |  | Reduce the time taken to prescribe regular medicines following confirmation of a medication history. | Quantitative | Time taken to prescribe regular medicines | Record the time taken from the point of medication history confirmation to point of medicines prescribing | Y
[7 empty] | System report |  | Y - when report available, at 3 monthly intervals.
[5 empty] | Qualitative | eMeds user survey
B2.1 | M2.1 | Quality and Clinical Governance |  | Clear and unambiguous prescriptions, useful annotations, clear who has written, amended or added comments to a prescription. | Quantitative | Number and type of chart changes/annotations. | Obtain drug charts from go-live wards for a 2 week period. Count occurrence and type of annotations. | Y | N/A
B2.1 | M2.2 | [5 empty] | Generate a system report to count the number of times a prescription has been changed. | N/A | Y - when report available, at 3 monthly intervals.
[5 empty] | Qualitative | eMeds user survey
|  | Quality and Clinical Governance | High | Reduced missed doses | Quantitative | Number of missed doses | Review Missed Doses Audit results | Y | N/A
[7 empty] | Drug chart audit on go-live wards: Number of missed doses and reason codes recorded on prescription charts over a 2 week period. | Y | N/A
[7 empty] | System report to highlight missed doses and reasons for omission. | N/A | Y - when report available, at 3 monthly intervals.
B9.4 | M7.5 | Quality and Clinical Governance |  | Improved compliance with antibiotic prescribing principles (duration and indication) | Quantitative | Antibiotic prescribing standards | Antibiotic audits | Y
[7 empty] | System report to highlight missing antibiotic prescription data | N/A | Y - when report available, at monthly intervals.
|  | Quality and Clinical Governance |  | Increased prescribing of MRSA decolonisation following risk assessment or positive MRSA result. | [7 empty] | Should measure include reduced MRSA bacteraemias? Success will depend on link from risk assessment.
|  | Quality and Clinical Governance |  | Data available for clinical audit.
|  | Quality and Clinical Governance |  | Data available for incident investigation
|  | Quality and Clinical Governance |  | Data available to monitor compliance with e.g. NICE guidance, medicines formulary.
|  | Quality and Clinical Governance | High | Improved patient experience as a result of a change in working practice, either from effiencies gained elsewhere or because WOWs support more patient focussed activity, compared to paper charts. | Qualitative | Improved Picker Survey results, Friends and Family test, reduced complaints | [5 empty] | Need to be clearer about what part of the patient experience will imporve.
|  | Operational Productivity | High | Increased awareness of formulary choices | Qualitative | eMeds user survey
B4.1 | M4.1 | Operational Productivity |  | More prescriptions for formulary medicines and fewer for non-formulary medicines. | Quantitative | Number of times non-formulary drugs are prescribed, as a proportion of all prescriptions. | Generate a system report to count the number of prescriptions for specified non-formulary medicines. Run the report before and after a medicine formulary change. | N/A
B4.1 | M4.2 | [5 empty] | Generate a system report to count: 1. The number of times a user has tried to prescribe a non-formulary drug. 2. The number of times the notification re a non-formulary drug has been over-ridden. | N/A | Y - when report available, at 3 monthly intervals.
B6.2 | M6.1 | Operational Productivity | High | Reduced time taken to order and receive medicines on the ward. | Qualitative | eMeds user survey |  |  | Y
B9.2 | M7.1 | Operational Productivity | High | Time savings and efficiencies as a consequence of reporting tools that simplify compliance monitoring. | Qualitative | eMeds user survey |  |  | Y |  |  | Need to replace the monthly paper anitmicrobial audit first.
B10.1 | M8.1 | Operational Productivity | High | Reductions in staff time wasted searching for drug charts. | Qualitative | eMeds user survey |  |  | Y
B14.1 | M9.1 | Operational Productivity | High | Reduction in time taken for medicine administration rounds | Qualitative | eMeds user survey |  |  | Y
|  | Operational Productivity | High | Medication data available as part of the electronic patient record | Qualitative | eMeds user survey | [5 empty] | How mediciation data from eMedicines is being viewed in or trasferred to other systems
|  | Operational Productivity |  | Reduced medicines costs resulting from targetted IV to oral switches. | Quantitative | [6 empty] | Any other measurable drug cost reductions?
|  | Operational Productivity |  | Improved medicines use data for non-tariff medicines and private patients leading to more accurate billing | Quantitative | [6 empty] | To d/w HT
|  | Operational Productivity |  | Reduced prescription stationery costs | Quantitative | Recorded spend on inpatient prescription charts, outpatient prescriptions (and TANs) | Compare costs before and after eMedicines implementation. | Y | Y